EAT40005 Internal Meeting Minutes
 Date: October 3, 2025
 Time: 2:00 PM – 3:00 PM
 Facilitator: Group Self-Organised
 Group: Group 1 – LIDA Mobile App Development Team
 Attendees:

- Chrishelle Anthoneyz

- Haritha Manuja Perera

- Thenura Kuruppuarachchi (Scrum Master)

- Senupama Deshapriya

### Agenda

- Reflect on client meeting (Oct 2, 7:30–8:00 PM)

- Finalise Sprint 3 priorities (GLB + sensor tabs + animations)

- Plan usability testing approach and survey

- Confirm deliverables and deadlines leading into Sprint 4

### Discussion Summary

#### Client Feedback → Team Decisions

- Sensor Tabs & Linking: Keep three tabs (Temperature, Moisture, Gases). Selecting an item (e.g., T1) must highlight the corresponding sensor on the 3D model and display the live value in the UI.

- GLB Integration: Current export shows named sensors correctly; polish highlighting and camera focus on selection.

- Animations: Proceed with animation plots; ensure they complement—not clutter—the interactive model.

- Testing: Prepare a short usability survey and recruit non-domain users for Week 11 testing.

#### Sprint 3 Focus (Remainings)

- Finish tab → model link (select in tab → highlight in 3D; and vice-versa if feasible).

- Improve colour rendering and ensure smooth model performance on mobile.

- Prepare MP4 demo showing tab interaction + model highlight.

- Draft usability survey and test plan.

### Task Assignments

- Thenura (Scrum Master)

  - Finalise GLB pipeline and implement sensor highlight + camera focus on selection.

  - Performance pass (model size, draw calls) for mobile.

- Haritha

  - Complete animation plots and expose simple play/pause control in the app.

  - Provide MP4 export for client review.

- Chrishelle

  - Draft usability survey (ease of navigation, clarity, task completion, SUS-style rating + 3–5 open questions).

  - Start user/technical documentation outline; keep Jira updated with acceptance criteria.

- Senupama

  - Build the tab UI (T, MC, Gases) with expand/collapse; render current values next to selected sensors.

  - Ensure code reads from a mock “live” source now, swappable to real data later.

### Testing & Documentation Plan

- Usability survey draft: ready by Oct 8 (Wed) for client glance.

- External user sessions (5–8 participants): Oct 20–24 (Week 11); collect scores + comments.

- Report & handover package (living doc): keep updating (GLB, MP4s, SolidWorks reference, manuals).

### Risks & Mitigations

- Live data access/format not final: use mock provider with same schema; switch to live when available.

- Mobile performance with GLB: reduce mesh complexity/textures; lazy-load animations.

- Time squeeze for testing: pre-book participants now; survey finalized by Oct 8.

### Deadlines & Next Steps

- Oct 7 (Tue): Tab→model highlighting working; MP4 demo exported.

- Oct 8 (Wed): Usability survey draft ready; share with client for quick OK.

- Oct 9–13: Polish colour rendering and camera focus; prep test build.

- Week 11 (Oct 20–24): Run usability sessions; compile results for Week 12 refinements.